## Slide 1: Flairdocs Workflow Designer Project
By the Null Pointers

## Slide 2: Project Mission and Objectives
Create a design tool help speed up creating customizable, automated workflows. By creating this product, system administrators will be able to make configurable workflows without the need of a software developer.
Usable
Configurable
Functional
Accessible

## Slide 5: Demo 1 Requirement Traceability Matrix

## Slide 6: Release Burndown Chart
Planned
Actual
Date | Iteration | Planned | Actual
9/22 | 0 | 123 | 123
9/29 | 1 | 123 | 123
10/6 | 2 | 108 | 100
10/13 | 3 | 92 | 
10/20 | 4 | 76 | 
10/27 | 5 | 60 | 
11/3 | 6 | 44 | 
11/10 | 7 | 28 | 
11/17 | 8 | 12 | 
11/24 | 9 | 0 | 

## Slide 7: Iteration Burnup Chart
Date | Planned | Actual | Added | Done
Prior | 15 | 1 | 0 | 1
9/29 | 15 | 4 | 0 | 3
9/30 | 15 | 6 | 0 | 2
10/1 | 15 | 9 | 0 | 3
10/2 | 23 | 12 | 8 | 3
10/3 | 23 | 15 | 0 | 3
10/4 | 23 | 15 | 0 | 0
10/5 | 23 | 23 | 0 | 8
10/6 | 23 | 23 | 0 | 0

## Slide 8: Defect Trend Chart
Date | Total Defects | Found | Closed
Prior | 0 | 0 | 0
9/29 | 0 | 0 | 0
9/30 | 0 | 0 | 0
10/1 | 0 | 0 | 0
10/2 | 0 | 0 | 0
10/3 | 0 | 0 | 0
10/4 | 0 | 0 | 0
10/5 | 0 | 0 | 0
10/6 | 0 | 0 | 0

## Slide 9: Regression Test Suite

## Slide 10: Live Demo